## 工作表1
ID | Defect Description | Backlog Num | Date | Final State | Comment
1 | logout sometimes not working | 3 | 2017-02-27 | Fixed
2 | No standard Email format requried | 2 | 2017-03-02 | Fixed
3 | Failure when illegally login | 1 | 2017-03-01 | Not Sure if attack
4 | timeline not works well | 7 | 2017-03-05 | Fixed
5 | The admin form resubmit after flash | 14 | 2017-03-19 | Fixed | Extra 2 hours
6 | Front end layout chaos after integration | 13 | 2017-03-20 | Most Fixed
7 | unknown warnings of post a coment | 2017-10-11 | 2017-03-20 | Fixed
8 | topics cannot display on index | 9 | 2017-03-21 | Fixed
1 | logout sometimes not working | 3 | 2017-03-21 | Fixed | When integrate Admin
9 | bugs of admin deleting reference key in category | 14 | 2017-03-22 | Fixed | When integrate Admin
10 | No character limit set for user name. | 2 | 2017-03-22 | Not Fixed